## HES-Sangai
Automation Status Summary
Project / Environment | Total Test Cases | Automated (On Server) | Pending Automation | Cannot be Automated | Automation Coverage (%)
HES-Sangai | 164 | 107 | 51 | 6 | 65.2439
Non-Automatable Test Cases
Test Case ID | Test Case Name / Description | Reason for Non-Automation | Manual/Alternative Validation Approach
DASH_002 | Validate redirection from HES Dashboard page to Jira Help Center and verify permission access control. | NA as per discussion with PM
MP_DL_006 | Verify HES Daily Load Collection When Meter RTC Is Corrupted | Cannot set curropt RTC in meter FW
CMD_TOU_007 | Verify TOD enegry Push at midnight on HES with corrupt RTC | Cannot set curropt RTC in meter FW
CMD_KEYS_001 | Verify LLS, HLS, and FW-HLS key setting command for all meter types in HES. | This scenario will be tested manually only as there is no command to read keys in HES
SINK_CHANGE_001 | Verify meter auto-mapping updates in HES and NMS when the parent DCU/IMG goes offline. | Manual interruption is needed
RF_FW_003 | Negative Scenarios – RF Firmware Upgrade Failure (Power OFF, DCU OFF, RF Module Removed, Invalid FW File) | Manual interruption is needed
Day-by-Day Automation Implementation Plan
Date | Project / Environment | Planned Test Cases | Automated Test Cases (Actual) | Cumulative Automated | Assigned To | Remarks
6/24/2026 | Sangai | 1 | 1 | 82 | Archi
7/14/2026 | Sangai | CMD_FW | 2 | 84 | Archi
7/20/2026 | Sangai | CMD_RF_FW | 2 | 86 | Archi
7/23/2026 | Sangai | CMD_LLT | 2 | 88 | Archi
7/28/2026 | Sangai | CMD_ | 10 | 98 | Archi
2026-06-08 | Sangai | RBAC_ | 33 | 131 | Archi
2026-10-08 | Sangai | CMD_LRC | 8 | 139 | Archi
2026-12-08 | Sangai | CMD_SCH | 3 | 142 | Archi
2026-12-08 | Sangai | EVT_DI | 3 | 145 | Archi
8/18/2026 | Sangai | DCU_FW | 19 | 164 | Archi
Project Completion Plan
Project / Environment | Total Test Cases | Total Duration (Days) | Daily Avg Execution | Start Date | Expected Completion Date | Status (On Track / Delayed)
Sangai | 164 | 48 | 3 | 2026-06-19 | 8/18/2026 | Delayed

## HES-Goamti
Automation Status Summary
Project / Environment | Total Test Cases | Automated (On Server) | Pending Automation | Cannot be Automated | Automation Coverage (%)
HES-Gomati | 164 | 133 | 25 | 6 | 81.0976
Non-Automatable Test Cases
Test Case ID | Test Case Name / Description | Reason for Non-Automation | Manual / Alternative Validation Approach
NA (6 Test Cases) | Environment/Scenario-specific test cases | Functional limitation / Manual validation required | Manual execution and verification
Day-by-Day Automation Implementation Plan
Date | Project / Environment | Planned Test Cases | Automated Test Cases (Actual) | Cumulative Automated | Assigned To | Remarks
2026-06-24 | Gomati | CMD_LLT | 2 | 101 | Archi
2026-07-02 | Gomati | CMD_RF_FW | 2 | 103 | Archi
2026-07-08 | Gomati | RBAC_ | 36 | 139 | Archi
2026-07-08 | Gomati | CMD_SCH | 4 | 143 | Archi
2026-08-10 | Gomati | CMD_LRC | 8 | 151 | Archi
2026-08-12 | Gomati | EVT_DI | 3 | 154 | Archi
2026-08-18 | Gomati | TOU | 10 | 164 | Archi
Project Completion Plan
Project / Environment | Total Test Cases | Total Duration (Days) | Daily Avg Execution | Start Date | Expected Completion Date | Status (On Track / Delayed)
Gomati | 168 | 48 | 3 | 2026-06-19 | 2026-08-18 | Delayed

## VEE
Automation Status Summary
Project / Environment | Total Test Cases | Automated (On Server) | Pending Automation | Cannot be Automated | Automation Coverage (%)
VEE Automation | 603 | 460(1PH - 212, 3PH - 248) | 119 | 24 | 80.56%
Non-Automatable Test Cases
Test Case ID | Test Case Name / Description | Reason for Non-Automation | Manual / Alternative Validation Approach
MRMB_473 | Daily Rollover Rule and Monthly Billing Estimation | Pending from Development Team | N/A
MRMB_474
MRMB_475
MRMB_476
DRDL_477
DRDL_478
DRDL_479
DRDL_480
DRMB_481
DRMB_482
DRMB_483
DRMB_484
DLPP_485
DLPP_486
DLPP_487
DLPP_488
DLPP_489
DLPP_490
DLPP_491
DLPP_492
UMIP_175
UMIP_176
UMBL_179
UMBL_180
UMDL_183
UMDL_184
UMMB_187
UMMB_188
MRBL_465
MRBL_466
MRBL_467
MRBL_468
Day-by-Day Automation Implementation Plan
Date | Project / Environment | Planned Test Cases | Automated Test Cases (Actual) | Cumulative Automated | Assigned To | Remarks
2026-07-13 | Gomati / Sangai | ERBL_XXX,ZCBL_XXX,UMBL_XXX | 30 | 30 | Arpit Jain | MDMS V1 development has been stopped. Test cases need to be updated as per the new database implementation.
2026-07-15 | Gomati / Sangai | HDIP_XXX, UMIP_XXX, ERIP_XXX, PFIP_XXX, MRIP_XXX | 216 | 246 | Arpit Jain | MDMS V1 development has been stopped. Test cases need to be updated as per the new database implementation.
2026-07-20 | Gomati / Sangai | HCDL_XXX, LCDL_XXX, NCDL_XXX, UMDL_XXX, SCBLDL_XXX, ZCDL_XXX, ERDL_XXX, MRDL_XXX | 118 | 364 | Arpit Jain | MDMS V1 development has been stopped. Test cases need to be updated as per the new database implementation.
2026-07-22 | Gomati / Sangai | HDMB_XXX, NCMB_XXX, UMMB_XXX, SCMB_XXX, ERMB_XXX, PFMB_XXX | 96 | 460 | Arpit Jain | MDMS V1 development has been stopped. Test cases need to be updated as per the new database implementation.
2026-09-11 | VEE UI | UIVRI_XXX, UIERI_XXX, UIFP_XXX, UIDAI_XXX, UIRVBL_XXX, UIRVDL_XXX, UIRVMB_XXX, UIRVIP_XXX, UIVSBL_XXX, UIVSDL_XXX, UIVSML_XXX, UIVSIP_XXX, UIESBL_XXX, UIESDL_XXX, UIESML_XXX, UIESIP_XXX, UIETDL_XXX, UIETIP_XXX, UIETIP_XXX, UIETTDL_XXX, UIETTBL_XXX, UIETTIP_XXX, UIDADL_XXX, UIDAMB_XXX, UIDABL_XXX, UIDAIP_XXX, UIDCBL_XXX, UIDCDL_XXX, UIDCMB_XXX, UIDCIP_XXX | 103 | N/A | Arpit Jain | Delayed Due to MDMS Release V2.7.1 Testing.
Start date - 24-07-2026
End date - 04-08-2026 (31-08-2026 -> shift to 11-09-2026)
Project Completion Plan
Project / Environment | Total Test Cases | Total Duration (Days) | Daily Avg Execution | Start Date | Expected Completion Date | Status (On Track / Delayed)
Gomati / Sangai | 603 | 45 (UI: 30 days tentative) | N/A | 2026-07-10 | 25/09/26 | Delayed

## Consumer_App
Automation Status Summary
Project / Environment | Total Test Cases | Automated (Current) | Pending Automation | Cannot be Automated | Automation Coverage (%)
Consumer App- Gomati (Android) | 88 | 48 | 30 | 10 | 61.54%
Non-Automatable Test Cases
Test Case ID | Test Case Name / Description | Reason for Non-Automation | Manual / Alternative Validation Approach
N/A | N/A | None identified | N/A
Day-by-Day Automation Implementation Plan
Date | Project / Environment | Planned Test Cases | Automated Test Cases (Actual) | Cumulative Automated | Assigned To | Remarks
2026-07-09 | Gomati(Android) | LOG_XXX | 4 | 4 | Komal Singhal | 2 Done, 2 Remaining
2026-07-15 | Gomati(Android) | HOM_XXX | 7 | 7 | Komal Singhal
2026-07-16 | Gomati(Android) | MMT_XXX | 9 | 9 | Komal Singhal | Done (2)
2026-07-20 | Gomati(Android) | SCU_XXX | 12 | 12 | Komal Singhal
2026-07-23 | Gomati(Android) | PRF_XXX | 17 | 17 | Komal Singhal | 3 Done, 2 Remaining
2026-08-11 | Gomati(Android) | MTR_XXX |  | 21 | Komal Singhal
2026-08-21 | Gomati(Android) | WLT_XXX |  | 40 | Komal Singhal | 10 Done, 9 Remaining
2026-08-24 | Gomati(Android) | BIL_XXX |  | 41 | Komal Singhal
2026-08-31 | Gomati(Android) | CNP_XXX |  | 47 | Komal Singhal
2026-09-01 | Gomati(Android) | SLD_XXX |  | 48 | Komal Singhal
2026-09-03 | Gomati(Android) | QKL_XXX |  | 51 | Komal Singhal
2026-09-04 | Gomati(Android) | TRF_XXX |  | 52 | Komal Singhal
2026-09-09 | Gomati(Android) | CSP_XXX |  | 53 | Komal Singhal
2026-09-10 | Gomati(Android) | FAQ_XXX |  | 54 | Komal Singhal
2026-09-14 | Gomati(Android) | MXD_XXX |  | 58 | Komal Singhal
2026-09-17 | Gomati(Android) | EBG_XXX |  | 59 | Komal Singhal
2026-09-18 | Gomati(Android) | UID_XXX |  | 60 | Komal Singhal
N/A | Gomati(Android) | DAR_XXX |  | 61 | Komal Singhal
2026-09-30 | Gomati(Android) | NTF_XXX |  | 69 | Komal Singhal
2026-10-01 | Gomati(Android) | SRH_XXX |  | 70 | Komal Singhal
2026-10-02 | Gomati(Android) | LNG_XXX |  | 71 | Komal Singhal
2026-10-05 | Gomati(Android) | STP_XXX |  | 72 | Komal Singhal
2026-10-06 | Gomati(Android) | GST_XXX |  | 75 | Komal Singhal
2026-10-08 | Gomati(Android) | PRV_XXX |  | 76 | Komal Singhal
2026-10-09 | Gomati(Android) | TNC_XXX |  | 77 | Komal Singhal
2026-10-12 | Gomati(Android) | EMP_XXX |  | 78 | Komal Singhal
2026-10-13 | Gomati(Android) | MUS_XXX |  | 79 | Komal Singhal
2026-10-15 | Gomati(Android) | PPD_XXX |  | 81 | Komal Singhal
Project Completion Plan
Project / Environment | Total Test Cases | Total Duration (Days) | Daily Avg Automation | Start Date | Expected Completion Date | Status
Gomati (Android) | 88 | 60 | 1.35 tc/d | 2026-07-09 | 2026-10-15 | Delayed

## Comms
Automation Status Summary
Project / Environment | Total Test Cases | Automated (On Server) | Pending Automation | Cannot be Automated | Automation Coverage (%)
Communication-Gomati | 89 | 43 | 0 | 46 | 48.3%
Non-Automatable Test Cases
Test Case ID | Test Case Name / Description | Reason for Non-Automation | Manual / Alternative Validation Approach
Network Validation (4 Test Cases) | Network Validation Scenarios | Hardware/Network dependency | Manual Validation
SIM Functionality (10 Test Cases) | SIM Operations & Validation | Requires physical SIM interaction | Manual Testing
Module Swapping (10 Test Cases) | Module Replacement & Swapping | Physical hardware replacement required | Manual Testing
Chattering Test (2 Test Cases) | Chattering Validation | Not feasible for automation | Manual Testing
Day-by-Day Automation Implementation Plan
Date | Project / Environment | Planned Test Cases / Module | Automated Test Cases (Actual) | Cumulative Automated | Assigned To | Remarks
2026-07-07 | Comms (4G / RF / IMG / DCU) | Provisioning | 5 | 5 | Saloni Sisodiya | Remaining provisioning automation
2026-07-07 | Comms (4G / RF / IMG / DCU) | Data Pull Test | 4 | 9 | Saloni Sisodiya | Remaining automation
2026-07-13 | Comms (4G / RF / IMG / DCU) | Data Push Test | 6 | 15 | Saloni Sisodiya | Remaining automation
2026-07-17 | Comms (4G / RF / IMG / DCU) | Network Validation- I | 2 | 17 | Saloni Sisodiya | Automatable network scenarios
2026-07-17 | Comms (4G / RF / IMG / DCU) | OTAP - I | 1 | 18 | Saloni Sisodiya | OTAP automation
2026-08-12 | Comms (4G / RF / IMG / DCU) | OTAP II | 13 | 31 | Saloni Sisodiya | OTAP automation
2026-08-19 | Comms (4G / RF / IMG / DCU) | Firmware Upgrade | 12 | 43 | Saloni Sisodiya | Firmware upgrade automation
2026-08-21 | Comms (4G / RF / IMG / DCU) | Power Cycle | 1 | 44 | Saloni Sisodiya | Power cycle validation
2026-08-27 | Comms (4G / RF / IMG / DCU) | Network Validation - II | 6 | 50 | Saloni Sisodiya | Automatable network scenarios
2026-09-03 | Comms (4G / RF / IMG / DCU) | SIM Functionality | 2 | 52 | Saloni Sisodiya | Limited automation possible
2026-09-05 | Comms (4G / RF / IMG / DCU) | RTC Sync | 1 | 58 | Saloni Sisodiya | RTC synchronization
2026-09-08 | Comms (4G / RF / IMG / DCU) | Network Latch | 2 | 60 | Saloni Sisodiya | Final automation completion
2026-09-15 | Comms (4G / RF / IMG / DCU) | Module Swapping | 5 | 57 | Saloni Sisodiya | Automatable scenarios only
Project Completion Plan
Project / Environment | Total Test Cases | Total Duration (Days) | Daily Avg Execution | Start Date | Expected Completion Date | Status (On Track / Delayed)
Comms (4G / RF / IMG / DCU) | 86 | 18 Calendar Days | ~3–4 Test Cases / Day | 2026-07-07 | 2026-09-15 | Delayed

## Firmware-Single_Phase
Automation Status Summary
Project / Environment | Total Test Cases | Automated (On Server) | Pending Automation | Cannot be Automated | Automation Coverage (%)
1-Phase | 806 | 79 | 727 | 0 | 9.801%
Non-Automatable Test Cases
Test Case ID | Test Case Name / Description | Reason for Non-Automation | Manual / Alternative Validation Approach
TBD | TBD | TBD | TBD
Day-by-Day Automation Implementation Plan
Date | Project / Environment | Planned Test Cases / Module | Automated Test Cases (Actual) | Cumulative Automated | Assigned To | Remarks
2026-08-28 | 1-Phase | Display | 25 | 25 | Nitesh
2026-08-28 | 1-Phase | Instantaneous (tap/HLDC) | 37 | 62 | Nitesh
2026-09-21 | 1-Phase | Maximum Demand | 36 | 98 | Saloni
2026-09-24 | 1-Phase | Block Load | 35 | 133 | Saloni
2026-09-29 | 1-Phase | Daily Load | 29 | 162 | Saloni
2026-10-05 | 1-Phase | Billing | 49 | 211 | Nitesh
2026-09-21 | 1-Phase | Communication | 6 | 217 | Dev
2026-08-31 | 1-Phase | Name Plate | 4 | 221 | Nitesh
2026-09-14 | 1-Phase | TAP | 105 | 326 | Nitesh
2026-10-08 | 1-Phase | TOD | 16 | 342 | Saloni
2026-09-28 | 1-Phase | FW Upgrade | 27 | 369 | Dev
2026-09-16 | 1-Phase | DLMS Association (HDLC) | 5 | 374 | Nitesh
2026-09-28 | 1-Phase | Tamper | 93 | 467 | Nitesh
2026-09-30 | 1-Phase | Factory Reset | 3 | 470 | Dev
2026-10-02 | 1-Phase | Neutral Missing | 3 | 473 | Dev
2026-10-08 | 1-Phase | RTC Effect | 13 | 486 | Dev
2026-10-12 | 1-Phase | Chattering | 4 | 490 | Dev
2026-09-30 | 1-Phase | AC chopping | 8 | 498 | Nitesh
2026-10-15 | 1-Phase | DC Pulsating | 8 | 506 | Dev
2026-10-20 | 1-Phase | DC Injection | 16 | 522 | Dev
2026-10-26 | 1-Phase | NIC Related | 15 | 537 | Dev
2026-10-02 | 1-Phase | 4G Fallback 2G | 6 | 543 | Nitesh
2026-10-27 | 1-Phase | Production | 1 | 544 | Dev
2026-10-05 | 1-Phase | Calibration | 3 | 547 | Nitesh
2026-10-29 | 1-Phase | Interruption | 4 | 551 | Dev
2026-11-02 | 1-Phase | Longrun | 2 | 553 | Dev
2026-11-05 | 1-Phase | Load Limit | 6 | 559 | Dev
2026-11-09 | 1-Phase | Power OFF | 5 | 564 | Dev
2026-10-15 | 1-Phase | Battery Consumption | 66 | 630 | Nitesh
2026-10-21 | 1-Phase | Transaction | 15 | 645 | Nitesh
2026-11-17 | 1-Phase | Periodic Push | 24 | 669 | Dev
2026-11-25 | 1-Phase | Event Push TAP RF | 24 | 693 | Dev
2026-12-02 | 1-Phase | Event Push 4G | 18 | 711 | Dev
2026-12-10 | 1-Phase | Periodic Push RF | 21 | 732 | Dev
2026-12-17 | 1-Phase | Event Push RF | 16 | 748 | Dev
2026-11-02 | 1-Phase | LRC (Local Relay Connection) | 33 | 781 | Nitesh
2026-11-05 | 1-Phase | TOD Push | 7 | 788 | Nitesh
2026-11-09 | 1-Phase | Bitmask | 4 | 792 | Nitesh
2026-11-18 | 1-Phase | Default Parameters | 14 | 806 | Nitesh
Project Completion Plan
Project / Environment | Total Test Cases | Total Duration (Days) | Daily Avg Automation | Start Date | Expected Completion Date | Status
1-Phase Meter Firmware | 806 | 150 | ~5 Test Cases / Calendar Day | 2026-08-16 | 2026-11-18 | On track

## Firmware-WC_LTCT
Automation Status Summary
Project / Environment | Total Test Cases | Automated (On Server) | Pending Automation | Cannot be Automated | Automation Coverage (%)
3-Phase | 476 | 0 | 451 | 0 | 0%
Non-Automatable Test Cases
Test Case ID | Test Case Name / Description | Reason for Non-Automation | Manual / Alternative Validation Approach
TBD | TBD | TBD | TBD
Day-by-Day Automation Implementation Plan
Date | Project / Environment | Planned Test Cases / Module | Automated Test Cases (Actual) | Cumulative Automated | Assigned To | Remarks
2026-10-10 | 3-Phase | Display | 25 | 25 | Nitesh
2026-12-22 | 3-Phase | Smoke Test | 2 | 27 | Nitesh
2026-12-29 | 3-Phase | Display | 5 | 32 | Nitesh
2026-12-31 | 3-Phase | Battery Mode Display | 3 | 35 | Nitesh
2026-12-21 | 3-Phase | Self Diagnostic | 3 | 38 | Dev
2027-01-04 | 3-Phase | Nameplate | 3 | 41 | Nitesh
2027-01-11 | 3-Phase | Instantaneous Parameter | 52 | 93 | Nitesh
2027-01-15 | 3-Phase | Rising Demand | 8 | 101 | Nitesh
2027-01-22 | 3-Phase | Maximum Demand | 10 | 111 | Nitesh
2027-01-28 | 3-Phase | Block Load | 22 | 133 | Nitesh
2027-02-04 | 3-Phase | Daily Load | 10 | 143 | Nitesh
2027-01-01 | 3-Phase | Billing Data | 50 | 193 | Dev
2027-01-08 | 3-Phase | TOD Data | 23 | 216 | Dev
2027-02-09 | 3-Phase | MD Reset Button | 4 | 220 | Nitesh
2027-02-15 | 3-Phase | Digital Input | 9 | 229 | Nitesh
2027-02-18 | 3-Phase | Tampers Voltage Related | 16 | 245 | Nitesh
2027-02-23 | 3-Phase | Tampers Current Related | 11 | 256 | Nitesh
2027-02-25 | 3-Phase | Tamper Other Related | 10 | 266 | Nitesh
2027-02-26 | 3-Phase | Tamper Non-Rollover | 1 | 267 | Nitesh
2027-01-12 | 3-Phase | Event Power Related | 2 | 269 | Dev
2027-01-22 | 3-Phase | Event_Transaction Related | 48 | 317 | Dev
2027-02-02 | 3-Phase | GPRS Testing | 15 | 332 | Dev
2027-02-08 | 3-Phase | Push Notification ESWF | 22 | 354 | Dev
2027-02-12 | 3-Phase | Firmware Upgrade | 22 | 376 | Dev
2027-03-02 | 3-Phase | Functions | 7 | 383 | Nitesh
2027-02-16 | 3-Phase | Interruption | 4 | 387 | Dev
2027-02-19 | 3-Phase | Chattering | 11 | 398 | Dev
2027-03-04 | 3-Phase | Calibration | 3 | 401 | Nitesh
2027-02-23 | 3-Phase | Harmonics | 7 | 408 | Dev
2027-03-09 | 3-Phase | Apparent Calculation | 11 | 419 | Nitesh
2027-03-12 | 3-Phase | DLMS Association & Push | 17 | 436 | Nitesh
2027-03-18 | 3-Phase | AC Chopping | 20 | 456 | Nitesh
2027-02-26 | 3-Phase | DC Injection & Pulsating | 16 | 472 | Dev
2027-03-01 | 3-Phase | Compartment | 1 | 473 | Dev
2027-03-19 | 3-Phase | Tamper Configuration | 3 | 476 | Nitesh
Project Completion Plan
Project / Environment | Total Test Cases | Total Duration (Days) | Daily Avg Automation | Start Date | Expected Completion Date | Status
3-Phase WC | 476 | 116 | ~5 Test Cases / Calendar Day | 2026-12-17 | 2027-03-19 | Not started Yet

## Meter Setu
Automation Status Summary
Project / Environment | Total Test Cases | Automated (On Server) | Pending Automation | Cannot be Automated | Automation Coverage (%)
Meter Setu-Gomati | 124 | 73 | 47 | 4 | 58.87%
Non-Automatable Test Cases
Test Case ID | Test Case Name / Description | Reason for Non-Automation | Manual / Alternative Validation Approach
MA-005 | USB Connection — DLMS handshake established | Needs a physical USB cable from phone to meter; the bench reaches meters over the TCP bridge, and plugging/unplugging is a physical action | Manual on a real phone with the probe cable; DLMS handshake itself covered over the bridge by INT-008
MA-010 | USB Connection — bottom sheet shows meter serial after connect | Sheet appears only on a real USB cable connect | Manual on a real phone with the probe cable
FW-009 | FOTA — block retry when probe is bumped / packet dropped | Probe must be physically misaligned during the transfer | Manual, during a supervised firmware upgrade
FW-010 | FOTA — cable detached mid-transfer shows interrupted state with Resume | Cable must be physically pulled at ~30% transfer | Manual, during a supervised firmware upgrade
Day-by-Day Automation Implementation Plan
Date | Project / Environment | Planned Test Cases / Module | Automated Test Cases (Actual) | Cumulative Automated | Assigned To | Remarks
2026-08-19 | Gomati — Stage/Dev | LG-005, LC-001, LC-013 | 3 | 3 | Shruti Singh | Executed — 2 Passed, 1 Failed
2026-08-26 | Gomati — Stage/Dev | LC-003 | 1 | 4 | Shruti Singh | Executed — Passed
2026-09-03 | Gomati — Stage/Dev | TC-001, TC-002, INT-008 | 3 | 7 | Shruti Singh | Executed — All Passed
2026-09-04 | Gomati — Stage/Dev | TC-011 | 1 | 8 | Shruti Singh | Executed — Passed
2026-09-07 | Gomati — Stage/Dev | LC-002, LC-006, LC-022 | 3 | 11 | Shruti Singh | Executed — 2 Passed, 1 Failed
2026-09-10 | Gomati — Stage/Dev | LC-004, LC-014 | 2 | 13 | Shruti Singh | Executed — 1 Passed, 1 Failed
2026-09-18 | Gomati — Stage/Dev | TC-003 | 1 | 14 | Shruti Singh | Executed — Passed
2026-09-21 | Gomati — Stage/Dev | SEC-002, LC-015, VAL-002, VAL-004 | 4 | 18 | Shruti Singh | Executed — All Passed
2026-09-22 | Gomati — Stage/Dev | LC-025, LC-026, LC-027, LC-028, LC-029 | 5 | 23 | Shruti Singh | Executed — All Passed
2026-09-25 | Gomati — Stage/Dev | LG-004, LG-006, TC-004, NEG-001, SEC-004, MA-011 | 6 | 29 | Shruti Singh | Executed — All Passed
2026-09-28 | Gomati — Stage/Dev | LC-010, LC-011 | 2 | 31 | Shruti Singh | Executed — All Passed
2026-09-30 | Gomati — Stage/Dev | LG-001, LG-003, AU-003, MA-001, MA-002, MA-004, DB-002, LC-008, LC-009, AU-005, VAL-005, INT-010, INT-011, LC-021 | 14 | 45 | Shruti Singh | Executed — All Passed
2026-10-01 | Gomati — Stage/Dev | LC-016, LC-018 | 2 | 47 | Shruti Singh | Executed — Metering Mode & MD Reset controls added in v1.2.20
2026-10-06 | Gomati — Stage/Dev | INT-001, VAL-003, LG-010, LG-002, TC-005, MA-006, DB-001, NEG-006, INT-009, LC-005, DB-003, NEG-003, MA-007, LC-007, LC-012, LC-019, LC-020, MA-008, MA-009 | 19 | 66 | Shruti Singh | Executed — known v1.2.20 defects fail LG-002, TC-005, MA-006, DB-001, NEG-006, INT-009, MA-007, LC-012
2026-10-14 | Gomati — Stage/Dev | LC-030, LC-031, LC-038 | 3 | 69 | Shruti Singh | Executed — new event & accuracy cards in 14-Oct v1.2.20 build
2026-10-22 | Gomati — Stage/Dev | INT-002, MA-003, FW-001, FW-002 | 4 | 73 | Shruti Singh | Executed — 2 Passed (MA-003, FW-002), 1 Failed (FW-001: no phase type on FOTA card), INT-002 rerun pending; INT-001 fixed for new WFM entry
2026-10-23 | Gomati — Stage/Dev | MA-012, NEG-004 | 0 | 73 | Shruti Singh | Planned — Screen rotation & DLMS failure mid-read
2026-10-26 | Gomati — Stage/Dev | MA-013, INT-012 | 0 | 73 | Shruti Singh | Planned — Meter tabs & Target Host IP (known v1.2.20 defects)
2026-10-27 | Gomati — Stage/Dev | LC-032, LC-033 | 0 | 73 | Shruti Singh | Planned — All Profile Read fresh read & Smart Skip
2026-10-28 | Gomati — Stage/Dev | LC-034, LC-036 | 0 | 73 | Shruti Singh | Planned — Smart Skip cache expiry & corrupt cache file
2026-10-29 | Gomati — Stage/Dev | LC-037, LC-023 | 0 | 73 | Shruti Singh | Planned — Cache per meter & per-meter Utility Settings controls
2026-10-30 | Gomati — Stage/Dev | DB-004, DB-005 | 0 | 73 | Shruti Singh | Planned — Offline CSV save & offline queue
2026-11-02 | Gomati — Stage/Dev | DB-006, DB-007 | 0 | 73 | Shruti Singh | Planned — Upload deletes local file & network loss during upload
2026-11-03 | Gomati — Stage/Dev | ST-001 | 0 | 73 | Shruti Singh | Planned — Background sync on internet restore
2026-11-03 | Gomati — Stage/Dev | All 124 cases | 0 | 73 | Shruti Singh | Planned — Full regression + DLMS verification + final report/email
TBD | Gomati — Stage/Dev | LG-007, LG-008, LG-009, AU-001, AU-002, AU-004, AU-006, SEC-001, SEC-003, NEG-002, INT-003, INT-004, INT-005, INT-006, INT-007, TC-006, TC-007, TC-008, TC-009, TC-010, ST-002, LC-017, LC-024, LC-035, VAL-001, FW-003, FW-004, FW-005, FW-006, FW-007, FW-008, FW-011 | 0 | 73 | Shruti Singh | On hold (30) — needs other-flavour APKs, Firebase config, Android 12 image, backend support, write/flash approval, WFM tickets that complete on the bench
Project Completion Plan
Project / Environment | Total Test Cases | Total Duration (Days) | Daily Avg Execution | Start Date | Expected Completion Date | Status
Gomati — Stage/Dev | 124 | 56 Working Days | 1.52 | 2026-08-18 | 2026-11-03 | ON TIME

## WFM
Automation Status Summary
Project / Environment | Total Test Cases | Automated (On Server) | Pending Automation | Cannot be Automated | Automation Coverage (%)
WFM Portal Stage | 278 | 117 | 6 | 155 | 42.09%
Non-Automatable Test Cases
Test Case ID | Test Case Name / Description | Reason for Non-Automation | Manual / Alternative Validation Approach
MA-003 | Mobile App – Offline Mode & Background Sync | Requires real device network toggling (Airplane Mode/Wi-Fi Off). Network state changes cannot be reliably automated in CI environments. | Perform validation on a physical Android device by disabling network, executing transactions, restoring connectivity, and verifying successful synchronization.
MA-008 | Mobile App – Prerequisite Form Upload with Photos & GPS | Requires physical camera and GPS hardware. Mock GPS providers are restricted by the application. | Capture images and GPS coordinates on a real device and verify successful upload.
MA-011 | Mobile App – Device Security Check (Rooted / Emulator Detection) | Requires a rooted Android device. Emulator execution cannot accurately validate root detection. | Validate on a rooted device and verify that the application blocks access with the appropriate security message.
MA-014 | Mobile App – Digital Signature Capture During SDUI Form Submission | Requires genuine handwriting input using finger or stylus. Automated gestures do not satisfy application validation. | Capture a signature on a physical device and verify successful storage and display.
ST-002 | Scheduled Tasks – Daily Productivity Report Generation (00:15) | Depends on a fixed scheduler and would require system time manipulation or midnight execution. | Verify the report after scheduled execution and confirm the generated timestamp.
SEC-003 | HTTPS Enforcement – HTTP Redirect to HTTPS | Infrastructure-level validation. Browser automation cannot reliably validate HTTP 301/302 redirects and HSTS headers. | Validate using Postman, curl, or Burp Suite.
Day-by-Day Automation Implementation Plan
Date | Project / Environment | Planned Test Cases / Module | Automated Test Cases (Actual) | Cumulative Automated | Assigned To | Remarks
2026-08-06 | WFM Portal – Stage (UP) | Login Module | 14 | 14 | Shruti Singh | Login module completed
2026-08-09 | WFM Portal – Stage (UP) | Dashboard Module | 5 | 19 | Shruti Singh | Dashboard module completed
2026-08-11 | WFM Portal – Stage (UP) | Ticket Report | 5 | 24 | Shruti Singh | Ticket Report completed
2026-08-11 | WFM Portal – Stage (UP) | Ticket Portal | 9 | 33 | Shruti Singh | Ticket Portal completed
2026-08-13 | WFM Portal – Stage (UP) | NOMC Portal | 6 | 39 | Shruti Singh | Planned
2026-08-15 | WFM Portal – Stage (UP) | QC Portal | 6 | 45 | Shruti Singh | Planned
2026-08-16 | WFM Portal – Stage (UP) | Manual Ticket | 4 | 49 | Shruti Singh | Planned
2026-08-18 | WFM Portal – Stage (UP) | Bulk Upload | 5 | 54 | Shruti Singh | Planned
2026-08-20 | WFM Portal – Stage (UP) | Exceptions | 5 | 59 | Shruti Singh | Planned
2026-08-22 | WFM Portal – Stage (UP) | Escalated Tickets | 5 | 64 | Shruti Singh | Planned
2026-08-24 | WFM Portal – Stage (UP) | Ticket Details | 6 | 70 | Shruti Singh | Planned
2026-08-26 | WFM Portal – Stage (UP) | Warehouse | 6 | 76 | Shruti Singh | Planned
2026-08-27 | WFM Portal – Stage (UP) | Factory File Upload | 3 | 79 | Shruti Singh | Planned
2026-08-29 | WFM Portal – Stage (UP) | Vendor Forward | 5 | 84 | Shruti Singh | Planned
2026-08-30 | WFM Portal – Stage (UP) | Vendor Return | 3 | 87 | Shruti Singh | Planned
2026-09-01 | WFM Portal – Stage (UP) | Vendor Material Inventory | 5 | 92 | Shruti Singh | Planned
2026-09-03 | WFM Portal – Stage (UP) | Material History | 4 | 96 | Shruti Singh | Planned
2026-09-05 | WFM Portal – Stage (UP) | Technician Management | 4 | 100 | Shruti Singh | Planned
2026-09-06 | WFM Portal – Stage (UP) | Vendor Profile | 4 | 104 | Shruti Singh | Planned
2026-09-08 | WFM Portal – Stage (UP) | Helpline 1912 Portal | 5 | 109 | Shruti Singh | Planned
2026-09-09 | WFM Portal – Stage (UP) | Productivity Report & Field Logs | 4 | 113 | Shruti Singh | Planned
2026-09-11 | WFM Portal – Stage (UP) | User Management | 6 | 119 | Shruti Singh | Planned
2026-09-13 | WFM Portal – Stage (UP) | Role & Module Permissions | 5 | 124 | Shruti Singh | Planned
2026-09-15 | WFM Portal – Stage (UP) | Geography & Category Management | 6 | 130 | Shruti Singh | Planned
2026-09-17 | WFM Portal – Stage (UP) | Action, Material Lifecycle & Material Type | 10 | 140 | Shruti Singh | Phase 1 completed
2026-09-19 | WFM Portal – Stage (UP) | Mobile App – Part 1 | 5 | 145 | Shruti Singh | Planned
2026-09-22 | WFM Portal – Stage (UP) | Mobile App – Part 2 | 5 | 150 | Shruti Singh | Planned
2026-09-24 | WFM Portal – Stage (UP) | Mobile App – Part 3 + Integration | 5 | 155 | Shruti Singh | Planned
2026-09-26 | WFM Portal – Stage (UP) | RBAC Module | 5 | 160 | Shruti Singh | Planned
2026-09-29 | WFM Portal – Stage (UP) | Validation Module | 5 | 165 | Shruti Singh | Planned
2026-10-01 | WFM Portal – Stage (UP) | Negative Testing – Part 1 | 5 | 170 | Shruti Singh | Planned
2026-10-05 | WFM Portal – Stage (UP) | Negative Testing – Part 2 | 5 | 175 | Shruti Singh | Planned
2026-10-07 | WFM Portal – Stage (UP) | User Onboarding & Concurrency | 5 | 180 | Shruti Singh | Planned
2026-10-09 | WFM Portal – Stage (UP) | SM-to-SM QC | 4 | 184 | Shruti Singh | Planned
2026-10-12 | WFM Portal – Stage (UP) | SLA & SDUI Builder – Part 1 | 5 | 189 | Shruti Singh | Planned
2026-10-14 | WFM Portal – Stage (UP) | SDUI, Ticket Source, Scheduled Tasks & Security | 5 | 194 | Shruti Singh | Planned
2026-10-16 | WFM Portal – Stage (UP) | Security, System Configuration & Return to Factory | 5 | 199 | Shruti Singh | Planned
2026-10-19 | WFM Portal – Stage (UP) | Return to Factory & Warehouse Configuration | 5 | 204 | Shruti Singh | Planned
2026-10-21 | WFM Portal – Stage (UP) | Warehouse Configuration & CIMI | 5 | 209 | Shruti Singh | Planned
2026-10-23 | WFM Portal – Stage (UP) | CIMI & Material Returns History | 5 | 214 | Shruti Singh | Planned
2026-10-26 | WFM Portal – Stage (UP) | Material Returns History, AWS & API Client | 5 | 219 | Shruti Singh | Planned
2026-10-28 | WFM Portal – Stage (UP) | API Client & App Updates | 5 | 224 | Shruti Singh | Planned
2026-10-30 | WFM Portal – Stage (UP) | Admin Vendor Management & Remaining Test Cases | 7 | 231 | Shruti Singh | Phase 2 completed
Project Completion Plan
Project / Environment | Total Test Cases | Total Duration (Days) | Daily Avg Execution | Start Date | Expected Completion Date | Status
WFM Portal Stage | 278 | On Hold | 2026-05-26 | TBD | Automation is temporarily on hold due to the current priority assignment for Meter Setu App testing. WFM automation will resume after completion of the current assignment. | On Hold

## Gomati_MDMS_RMS
Automation Status Summary
Project / Environment | Total Test Cases | Automated (On Server) | Pending Automation | Cannot be Automated | Automation Coverage (%)
Gomati -MDMS-RMS | 131 | 0 | 108 | 23 | 100%
Non-Automatable Test Cases
Test Case ID | Test Case Name / Description | Reason for Non-Automation | Manual / Alternative Validation Approach
BDS_003 | SFTP/CSV billing data delivery (semicolon-separated, Normal Meter) | Describes an SFTP file delivery, not a call to /odr_billing/. No HTTP request exists to make. | Pull the delivered file from the SFTP drop and check the record layout manually, or add a separate SFTP client.
BDS_004 | SFTP/CSV billing data delivery (comma-separated, Net Meter / Net Bill) | File delivery is outside the REST surface. | Manual file pull and layout check.
BDS_005 | 4-TOD-slot billing data (HV2 / LMV6 / LMV11) | Requires validating CSV content, not an HTTP response. | Open the delivered CSV and verify the four TOD slot columns per tariff.
BDS_006 | 2-TOD-slot billing data (LMV3) | Requires validating CSV content, not an HTTP response. | Open the delivered CSV and verify the two TOD slot columns.
BDS_007 | Boundary: billing-data CSV field lengths and precision (doc Sec 4) | Sec 4 field tables describe columns in MDM's monthly CSV delivery, not fields on an endpoint. | Field-by-field check against Sec 4 on a sample delivery file.
MADV_001 | Non-Smart to Smart meter replacement advised via WFM | Meter Advising has no endpoint in the v2.0.6 OpenAPI spec. SFTP/CSV flow and billing happen inside CC&B. | Verify in WFM and CC&B directly, with the advice file as evidence.
MADV_002 | TOD-register re-mapping on old/new meter slot boundary mismatch | SFTP/CSV flow with no REST endpoint exposed. | Compare the old and new register maps in MDMS after a replacement.
MADV_003 | Negative: Meter Advice CSV validation failures routed to Error folder | Asserts on file routing between SFTP folders. Nothing HTTP to observe. | Drop a deliberately malformed advice file and confirm it lands in the Error folder.
MADV_004 | Remaining flag fields (reference row) | A reference row inside a module that has no endpoint. | Covered by the manual MADV checks above.
MADV_005 | Boundary: MADV field length / range / precision (doc Sec 3.2) | Field tables describe CSV columns, not request payload fields. | Field-by-field check against Sec 3.2 on a sample advice file.
NFR_003 | REST vs SOAP response contract consistency | The live spec exposes REST/JSON only. A SOAP interface would need its own client and test set. | Confirm with the integration team whether a SOAP interface is in scope.
SLA_003 | Monthly Billing Data (CSV/SFTP) delivery SLA | Measures timeliness of a file delivery to CC&B, with no REST call to time. | Track delivery timestamps on the SFTP drop across a billing cycle.
NFR_004 | Real-time master data sync consistency across sync-type APIs | Partially automatable. The suite sends the data, but confirming what landed needs a read-back endpoint that MDMS does not expose. | Spot-check in the MDMS UI, or request a GET/query endpoint so the assertion can be automated.
ABR_005, ANEC_003, IMDS_039, MBNV_003, MFC_003, NFR_005, NNBC_003, NNMC_003, PBE_003, SLA_004 | Reference rows in the source workbook (10 IDs) | Not test cases. They describe or cross-reference other cases rather than specifying a test. | None required.
Day-by-Day Automation Implementation Plan
Date | Project / Environment | Planned Test Cases / Module | Automated Test Cases (Actual) | Cumulative Automated | Assigned To | Remarks
2026-08-17 | MDMS | Initial Master Data Sync | 27 | 27 | Shanvi | 25 PASS, 2 FAIL
2026-08-18 | MDMS | Initial Master Data Sync + Attribute Change | 23 | 50 | Shanvi | 18 PASS, 5 FAIL, 1 Not Automatable
2026-08-19 | MDMS | Attribute Change + Accept Prepaid Recharge + Account Balance Reconciliation + Reconnection & Disconnection + Arrear Payment Sync + Accept Non-Energy Charges | 25 | 75 | Shanvi | 24 PASS, 1 FAIL, 1 Not Automatable
2026-08-20 | MDMS | Non-Energy Charges Payment Sync + Postpaid-Prepaid Conversion + Smart Meter to Smart Meter Change + Prepaid Balance Enquiry + Normal to Net Meter Change + Normal to Net Bill Change + Multiplying Factor Change | 22 | 97 | Shanvi | 20 PASS, 2 FAIL, 5 Not Automatable
2026-08-21 | MDMS | Multiplying Factor Change + Billing Data Sync + Meter Badge Number Validation + Cross-Cutting NFR + Meter Advising + SAT/SLA Acceptance Criteria | 9 | 106 | Shanvi | 5 PASS, 4 FAIL, 10 Not Automatable
Project Completion Plan
Project / Environment | Total Test Cases | Total Duration (Days) | Daily Avg Execution | Start Date | Expected Completion Date | Status (On Track / Delayed)
Gomati -MDMS-RMS | 131 | 5 Working Days | ~26 Test Cases/Day | 2026-08-17 | Not Given | Delayed