## Projects
id | name | total_cases | automatable | non_automatable | automated | in_progress | team_size | start_date | target_date | daily_avg | status | priority | color | notes
hes_sangai | HES-Sangai | 164 | 158 | 6 | 107 | 0 | 1 | 2026-06-19 | 2026-08-18 | 3 | Delayed | Medium | #7c3aed
hes_goamti | HES-Gomati | 164 | 158 | 6 | 133 | 0 | 1 | 2026-06-19 | 2026-08-18 | 3 | Delayed | Medium | #0891b2
vee | VEE Automation | 603 | 579 | 24 | 460 | 0 | 1 | 2026-07-10 | 2026-09-25 | 0 | Delayed | Medium | #ea580c
consumer_app | Consumer App- Gomati (Android) | 88 | 78 | 10 | 48 | 0 | 1 | 2026-07-09 | 2026-10-15 | 1.35 | Delayed | Medium | #059669
comms | Communication-Gomati | 89 | 43 | 46 | 43 | 0 | 1 | 2026-07-07 | 2026-09-15 | 3 | Delayed | Medium | #f59e0b
firmware_single_phase | 1-Phase | 806 | 806 | 0 | 79 | 0 | 1 | 2026-08-16 | 2026-11-18 | 5 | On Track | Medium | #db2777
firmware_wc_ltct | 3-Phase | 476 | 476 | 0 | 0 | 0 | 1 | 2026-12-17 | 2027-03-19 | 5 | Not Started | Medium | #ea580c
meter_setu | Meter Setu-Gomati | 124 | 120 | 4 | 73 | 0 | 1 | 2026-08-18 | 2026-11-03 | 1.52 | On Track | Medium | #dc2626
wfm | WFM Portal Stage | 278 | 123 | 155 | 117 | 0 | 1 | TBD | TBD | 0 | On Hold | Medium | #64748b
gomati_mdms_rms | Gomati -MDMS-RMS | 131 | 108 | 23 | 0 | 0 | 1 | 2026-08-17 | Not Given | 26 | Delayed | Medium | #64748b

## Non_Automatable
project_id | module | count | reason | approach
hes_sangai | DASH_002 | 1 | NA as per discussion with PM
hes_sangai | MP_DL_006 | 1 | Cannot set curropt RTC in meter FW
hes_sangai | CMD_TOU_007 | 1 | Cannot set curropt RTC in meter FW
hes_sangai | CMD_KEYS_001 | 1 | This scenario will be tested manually only as there is no command to read keys in HES
hes_sangai | SINK_CHANGE_001 | 1 | Manual interruption is needed
hes_sangai | RF_FW_003 | 1 | Manual interruption is needed
hes_goamti | NA (6 Test Cases) | 6 | Functional limitation / Manual validation required | Manual execution and verification
vee | MRMB_473 | 1 | Pending from Development Team
vee | MRMB_474 | 1
vee | MRMB_475 | 1
vee | MRMB_476 | 1
vee | DRDL_477 | 1
vee | DRDL_478 | 1
vee | DRDL_479 | 1
vee | DRDL_480 | 1
vee | DRMB_481 | 1
vee | DRMB_482 | 1
vee | DRMB_483 | 1
vee | DRMB_484 | 1
vee | DLPP_485 | 1
vee | DLPP_486 | 1
vee | DLPP_487 | 1
vee | DLPP_488 | 1
vee | DLPP_489 | 1
vee | DLPP_490 | 1
vee | DLPP_491 | 1
vee | DLPP_492 | 1
vee | UMIP_175 | 1
vee | UMIP_176 | 1
vee | UMBL_179 | 1
vee | UMBL_180 | 1
vee | UMDL_183 | 1
vee | UMDL_184 | 1
vee | UMMB_187 | 1
vee | UMMB_188 | 1
vee | MRBL_465 | 1
vee | MRBL_466 | 1
vee | MRBL_467 | 1
vee | MRBL_468 | 1
comms | Network Validation (4 Test Cases) | 4 | Hardware/Network dependency | Manual Validation
comms | SIM Functionality (10 Test Cases) | 10 | Requires physical SIM interaction | Manual Testing
comms | Module Swapping (10 Test Cases) | 10 | Physical hardware replacement required | Manual Testing
comms | Chattering Test (2 Test Cases) | 2 | Not feasible for automation | Manual Testing
firmware_single_phase | TBD | 1 | TBD | TBD
firmware_wc_ltct | TBD | 1 | TBD | TBD
meter_setu | MA-005 | 1 | Needs a physical USB cable from phone to meter; the bench reaches meters over the TCP bridge, and plugging/unplugging is a physical action | Manual on a real phone with the probe cable; DLMS handshake itself covered over the bridge by INT-008
meter_setu | MA-010 | 1 | Sheet appears only on a real USB cable connect | Manual on a real phone with the probe cable
meter_setu | FW-009 | 1 | Probe must be physically misaligned during the transfer | Manual, during a supervised firmware upgrade
meter_setu | FW-010 | 1 | Cable must be physically pulled at ~30% transfer | Manual, during a supervised firmware upgrade
wfm | MA-003 | 1 | Requires real device network toggling (Airplane Mode/Wi-Fi Off). Network state changes cannot be reliably automated in CI environments. | Perform validation on a physical Android device by disabling network, executing transactions, restoring connectivity, and verifying successful synchronization.
wfm | MA-008 | 1 | Requires physical camera and GPS hardware. Mock GPS providers are restricted by the application. | Capture images and GPS coordinates on a real device and verify successful upload.
wfm | MA-011 | 1 | Requires a rooted Android device. Emulator execution cannot accurately validate root detection. | Validate on a rooted device and verify that the application blocks access with the appropriate security message.
wfm | MA-014 | 1 | Requires genuine handwriting input using finger or stylus. Automated gestures do not satisfy application validation. | Capture a signature on a physical device and verify successful storage and display.
wfm | ST-002 | 1 | Depends on a fixed scheduler and would require system time manipulation or midnight execution. | Verify the report after scheduled execution and confirm the generated timestamp.
wfm | SEC-003 | 1 | Infrastructure-level validation. Browser automation cannot reliably validate HTTP 301/302 redirects and HSTS headers. | Validate using Postman, curl, or Burp Suite.
gomati_mdms_rms | BDS_003 | 1 | Describes an SFTP file delivery, not a call to /odr_billing/. No HTTP request exists to make. | Pull the delivered file from the SFTP drop and check the record layout manually, or add a separate SFTP client.
gomati_mdms_rms | BDS_004 | 1 | File delivery is outside the REST surface. | Manual file pull and layout check.
gomati_mdms_rms | BDS_005 | 1 | Requires validating CSV content, not an HTTP response. | Open the delivered CSV and verify the four TOD slot columns per tariff.
gomati_mdms_rms | BDS_006 | 1 | Requires validating CSV content, not an HTTP response. | Open the delivered CSV and verify the two TOD slot columns.
gomati_mdms_rms | BDS_007 | 1 | Sec 4 field tables describe columns in MDM's monthly CSV delivery, not fields on an endpoint. | Field-by-field check against Sec 4 on a sample delivery file.
gomati_mdms_rms | MADV_001 | 1 | Meter Advising has no endpoint in the v2.0.6 OpenAPI spec. SFTP/CSV flow and billing happen inside CC&B. | Verify in WFM and CC&B directly, with the advice file as evidence.
gomati_mdms_rms | MADV_002 | 1 | SFTP/CSV flow with no REST endpoint exposed. | Compare the old and new register maps in MDMS after a replacement.
gomati_mdms_rms | MADV_003 | 1 | Asserts on file routing between SFTP folders. Nothing HTTP to observe. | Drop a deliberately malformed advice file and confirm it lands in the Error folder.
gomati_mdms_rms | MADV_004 | 1 | A reference row inside a module that has no endpoint. | Covered by the manual MADV checks above.
gomati_mdms_rms | MADV_005 | 1 | Field tables describe CSV columns, not request payload fields. | Field-by-field check against Sec 3.2 on a sample advice file.
gomati_mdms_rms | NFR_003 | 1 | The live spec exposes REST/JSON only. A SOAP interface would need its own client and test set. | Confirm with the integration team whether a SOAP interface is in scope.
gomati_mdms_rms | SLA_003 | 1 | Measures timeliness of a file delivery to CC&B, with no REST call to time. | Track delivery timestamps on the SFTP drop across a billing cycle.
gomati_mdms_rms | NFR_004 | 1 | Partially automatable. The suite sends the data, but confirming what landed needs a read-back endpoint that MDMS does not expose. | Spot-check in the MDMS UI, or request a GET/query endpoint so the assertion can be automated.
gomati_mdms_rms | ABR_005, ANEC_003, IMDS_039, MBNV_003, MFC_003, NFR_005, NNBC_003, NNMC_003, PBE_003, SLA_004 | 10 | Not test cases. They describe or cross-reference other cases rather than specifying a test. | None required.

## Day_Plan
project_id | date | module | planned_cases | actual_cases | cumulative | assigned_to | remarks | status
hes_sangai | 2026-06-24 | 1 | 1 | 1 | 82 | Archi |  | Completed
hes_sangai | 2026-07-14 | CMD_FW | 2 | 2 | 84 | Archi |  | Completed
hes_sangai | 2026-07-20 | CMD_RF_FW | 2 | 2 | 86 | Archi |  | Completed
hes_sangai | 2026-07-23 | CMD_LLT | 2 | 2 | 88 | Archi |  | Completed
hes_sangai | 2026-07-28 | CMD_ | 10 | 10 | 98 | Archi |  | Completed
hes_sangai | 2026-06-08 | RBAC_ | 33 | 33 | 131 | Archi |  | Completed
hes_sangai | 2026-10-08 | CMD_LRC | 8 | 8 | 139 | Archi |  | Completed
hes_sangai | 2026-12-08 | CMD_SCH | 3 | 3 | 142 | Archi |  | Completed
hes_sangai | 2026-12-08 | EVT_DI | 3 | 3 | 145 | Archi |  | Completed
hes_sangai | 2026-08-18 | DCU_FW | 19 | 19 | 164 | Archi |  | Completed
hes_goamti | 2026-06-24 | CMD_LLT | 2 | 2 | 101 | Archi |  | Completed
hes_goamti | 2026-07-02 | CMD_RF_FW | 2 | 2 | 103 | Archi |  | Completed
hes_goamti | 2026-07-08 | RBAC_ | 36 | 36 | 139 | Archi |  | Completed
hes_goamti | 2026-07-08 | CMD_SCH | 4 | 4 | 143 | Archi |  | Completed
hes_goamti | 2026-08-10 | CMD_LRC | 8 | 8 | 151 | Archi |  | Completed
hes_goamti | 2026-08-12 | EVT_DI | 3 | 3 | 154 | Archi |  | Completed
hes_goamti | 2026-08-18 | TOU | 10 | 10 | 164 | Archi |  | Completed
vee | 2026-07-13 | ERBL_XXX,ZCBL_XXX,UMBL_XXX | 30 | 30 | 30 | Arpit Jain | MDMS V1 development has been stopped. Test cases need to be updated as per the new database implementation. | Completed
vee | 2026-07-15 | HDIP_XXX, UMIP_XXX, ERIP_XXX, PFIP_XXX, MRIP_XXX | 216 | 216 | 246 | Arpit Jain | MDMS V1 development has been stopped. Test cases need to be updated as per the new database implementation. | Completed
vee | 2026-07-20 | HCDL_XXX, LCDL_XXX, NCDL_XXX, UMDL_XXX, SCBLDL_XXX, ZCDL_XXX, ERDL_XXX, MRDL_XXX | 118 | 118 | 364 | Arpit Jain | MDMS V1 development has been stopped. Test cases need to be updated as per the new database implementation. | Completed
vee | 2026-07-22 | HDMB_XXX, NCMB_XXX, UMMB_XXX, SCMB_XXX, ERMB_XXX, PFMB_XXX | 96 | 96 | 460 | Arpit Jain | MDMS V1 development has been stopped. Test cases need to be updated as per the new database implementation. | Completed
vee | 2026-09-11 | UIVRI_XXX, UIERI_XXX, UIFP_XXX, UIDAI_XXX, UIRVBL_XXX, UIRVDL_XXX, UIRVMB_XXX, UIRVIP_XXX, UIVSBL_XXX, UIVSDL_XXX, UIVSML_XXX, UIVSIP_XXX, UIESBL_XXX, UIESDL_XXX, UIESML_XXX, UIESIP_XXX, UIETDL_XXX, UIETIP_XXX, UIETIP_XXX, UIETTDL_XXX, UIETTBL_XXX, UIETTIP_XXX, UIDADL_XXX, UIDAMB_XXX, UIDABL_XXX, UIDAIP_XXX, UIDCBL_XXX, UIDCDL_XXX, UIDCMB_XXX, UIDCIP_XXX | 103 | 103 | 0 | Arpit Jain | Delayed Due to MDMS Release V2.7.1 Testing. | Completed
consumer_app | 2026-07-09 | LOG_XXX | 4 | 4 | 4 | Komal Singhal | 2 Done, 2 Remaining | Completed
consumer_app | 2026-07-15 | HOM_XXX | 7 | 7 | 7 | Komal Singhal |  | Completed
consumer_app | 2026-07-16 | MMT_XXX | 9 | 9 | 9 | Komal Singhal | Done (2) | Completed
consumer_app | 2026-07-20 | SCU_XXX | 12 | 12 | 12 | Komal Singhal |  | Completed
consumer_app | 2026-07-23 | PRF_XXX | 17 | 17 | 17 | Komal Singhal | 3 Done, 2 Remaining | Completed
consumer_app | 2026-08-11 | MTR_XXX | 0 | 0 | 21 | Komal Singhal |  | Planned
consumer_app | 2026-08-21 | WLT_XXX | 0 | 0 | 40 | Komal Singhal | 10 Done, 9 Remaining | Planned
consumer_app | 2026-08-24 | BIL_XXX | 0 | 0 | 41 | Komal Singhal |  | Planned
consumer_app | 2026-08-31 | CNP_XXX | 0 | 0 | 47 | Komal Singhal |  | Planned
consumer_app | 2026-09-01 | SLD_XXX | 0 | 0 | 48 | Komal Singhal |  | Planned
consumer_app | 2026-09-03 | QKL_XXX | 0 | 0 | 51 | Komal Singhal |  | Planned
consumer_app | 2026-09-04 | TRF_XXX | 0 | 0 | 52 | Komal Singhal |  | Planned
consumer_app | 2026-09-09 | CSP_XXX | 0 | 0 | 53 | Komal Singhal |  | Planned
consumer_app | 2026-09-10 | FAQ_XXX | 0 | 0 | 54 | Komal Singhal |  | Planned
consumer_app | 2026-09-14 | MXD_XXX | 0 | 0 | 58 | Komal Singhal |  | Planned
consumer_app | 2026-09-17 | EBG_XXX | 0 | 0 | 59 | Komal Singhal |  | Planned
consumer_app | 2026-09-18 | UID_XXX | 0 | 0 | 60 | Komal Singhal |  | Planned
consumer_app |  | DAR_XXX | 0 | 0 | 61 | Komal Singhal |  | Planned
consumer_app | 2026-09-30 | NTF_XXX | 0 | 0 | 69 | Komal Singhal |  | Planned
consumer_app | 2026-10-01 | SRH_XXX | 0 | 0 | 70 | Komal Singhal |  | Planned
consumer_app | 2026-10-02 | LNG_XXX | 0 | 0 | 71 | Komal Singhal |  | Planned
consumer_app | 2026-10-05 | STP_XXX | 0 | 0 | 72 | Komal Singhal |  | Planned
consumer_app | 2026-10-06 | GST_XXX | 0 | 0 | 75 | Komal Singhal |  | Planned
consumer_app | 2026-10-08 | PRV_XXX | 0 | 0 | 76 | Komal Singhal |  | Planned
consumer_app | 2026-10-09 | TNC_XXX | 0 | 0 | 77 | Komal Singhal |  | Planned
consumer_app | 2026-10-12 | EMP_XXX | 0 | 0 | 78 | Komal Singhal |  | Planned
consumer_app | 2026-10-13 | MUS_XXX | 0 | 0 | 79 | Komal Singhal |  | Planned
consumer_app | 2026-10-15 | PPD_XXX | 0 | 0 | 81 | Komal Singhal |  | Planned
comms | 2026-07-07 | Provisioning | 5 | 5 | 5 | Saloni Sisodiya | Remaining provisioning automation | Completed
comms | 2026-07-07 | Data Pull Test | 4 | 4 | 9 | Saloni Sisodiya | Remaining automation | Completed
comms | 2026-07-13 | Data Push Test | 6 | 6 | 15 | Saloni Sisodiya | Remaining automation | Completed
comms | 2026-07-17 | Network Validation- I | 2 | 2 | 17 | Saloni Sisodiya | Automatable network scenarios | Completed
comms | 2026-07-17 | OTAP - I | 1 | 1 | 18 | Saloni Sisodiya | OTAP automation | Completed
comms | 2026-08-12 | OTAP II | 13 | 13 | 31 | Saloni Sisodiya | OTAP automation | Completed
comms | 2026-08-19 | Firmware Upgrade | 12 | 12 | 43 | Saloni Sisodiya | Firmware upgrade automation | Completed
comms | 2026-08-21 | Power Cycle | 1 | 1 | 44 | Saloni Sisodiya | Power cycle validation | Completed
comms | 2026-08-27 | Network Validation - II | 6 | 6 | 50 | Saloni Sisodiya | Automatable network scenarios | Completed
comms | 2026-09-03 | SIM Functionality | 2 | 2 | 52 | Saloni Sisodiya | Limited automation possible | Completed
comms | 2026-09-05 | RTC Sync | 1 | 1 | 58 | Saloni Sisodiya | RTC synchronization | Completed
comms | 2026-09-08 | Network Latch | 2 | 2 | 60 | Saloni Sisodiya | Final automation completion | Completed
comms | 2026-09-15 | Module Swapping | 5 | 5 | 57 | Saloni Sisodiya | Automatable scenarios only | Completed
firmware_single_phase | 2026-08-28 | Display | 25 | 25 | 25 | Nitesh |  | Completed
firmware_single_phase | 2026-08-28 | Instantaneous (tap/HLDC) | 37 | 37 | 62 | Nitesh |  | Completed
firmware_single_phase | 2026-09-21 | Maximum Demand | 36 | 36 | 98 | Saloni |  | Completed
firmware_single_phase | 2026-09-24 | Block Load | 35 | 35 | 133 | Saloni |  | Completed
firmware_single_phase | 2026-09-29 | Daily Load | 29 | 29 | 162 | Saloni |  | Completed
firmware_single_phase | 2026-10-05 | Billing | 49 | 49 | 211 | Nitesh |  | Completed
firmware_single_phase | 2026-09-21 | Communication | 6 | 6 | 217 | Dev |  | Completed
firmware_single_phase | 2026-08-31 | Name Plate | 4 | 4 | 221 | Nitesh |  | Completed
firmware_single_phase | 2026-09-14 | TAP | 105 | 105 | 326 | Nitesh |  | Completed
firmware_single_phase | 2026-10-08 | TOD | 16 | 16 | 342 | Saloni |  | Completed
firmware_single_phase | 2026-09-28 | FW Upgrade | 27 | 27 | 369 | Dev |  | Completed
firmware_single_phase | 2026-09-16 | DLMS Association (HDLC) | 5 | 5 | 374 | Nitesh |  | Completed
firmware_single_phase | 2026-09-28 | Tamper | 93 | 93 | 467 | Nitesh |  | Completed
firmware_single_phase | 2026-09-30 | Factory Reset | 3 | 3 | 470 | Dev |  | Completed
firmware_single_phase | 2026-10-02 | Neutral Missing | 3 | 3 | 473 | Dev |  | Completed
firmware_single_phase | 2026-10-08 | RTC Effect | 13 | 13 | 486 | Dev |  | Completed
firmware_single_phase | 2026-10-12 | Chattering | 4 | 4 | 490 | Dev |  | Completed
firmware_single_phase | 2026-09-30 | AC chopping | 8 | 8 | 498 | Nitesh |  | Completed
firmware_single_phase | 2026-10-15 | DC Pulsating | 8 | 8 | 506 | Dev |  | Completed
firmware_single_phase | 2026-10-20 | DC Injection | 16 | 16 | 522 | Dev |  | Completed
firmware_single_phase | 2026-10-26 | NIC Related | 15 | 15 | 537 | Dev |  | Completed
firmware_single_phase | 2026-10-02 | 4G Fallback 2G | 6 | 6 | 543 | Nitesh |  | Completed
firmware_single_phase | 2026-10-27 | Production | 1 | 1 | 544 | Dev |  | Completed
firmware_single_phase | 2026-10-05 | Calibration | 3 | 3 | 547 | Nitesh |  | Completed
firmware_single_phase | 2026-10-29 | Interruption | 4 | 4 | 551 | Dev |  | Completed
firmware_single_phase | 2026-11-02 | Longrun | 2 | 2 | 553 | Dev |  | Completed
firmware_single_phase | 2026-11-05 | Load Limit | 6 | 6 | 559 | Dev |  | Completed
firmware_single_phase | 2026-11-09 | Power OFF | 5 | 5 | 564 | Dev |  | Completed
firmware_single_phase | 2026-10-15 | Battery Consumption | 66 | 66 | 630 | Nitesh |  | Completed
firmware_single_phase | 2026-10-21 | Transaction | 15 | 15 | 645 | Nitesh |  | Completed
firmware_single_phase | 2026-11-17 | Periodic Push | 24 | 24 | 669 | Dev |  | Completed
firmware_single_phase | 2026-11-25 | Event Push TAP RF | 24 | 24 | 693 | Dev |  | Completed
firmware_single_phase | 2026-12-02 | Event Push 4G | 18 | 18 | 711 | Dev |  | Completed
firmware_single_phase | 2026-12-10 | Periodic Push RF | 21 | 21 | 732 | Dev |  | Completed
firmware_single_phase | 2026-12-17 | Event Push RF | 16 | 16 | 748 | Dev |  | Completed
firmware_single_phase | 2026-11-02 | LRC (Local Relay Connection) | 33 | 33 | 781 | Nitesh |  | Completed
firmware_single_phase | 2026-11-05 | TOD Push | 7 | 7 | 788 | Nitesh |  | Completed
firmware_single_phase | 2026-11-09 | Bitmask | 4 | 4 | 792 | Nitesh |  | Completed
firmware_single_phase | 2026-11-18 | Default Parameters | 14 | 14 | 806 | Nitesh |  | Completed
firmware_wc_ltct | 2026-10-10 | Display | 25 | 25 | 25 | Nitesh |  | Completed
firmware_wc_ltct | 2026-12-22 | Smoke Test | 2 | 2 | 27 | Nitesh |  | Completed
firmware_wc_ltct | 2026-12-29 | Display | 5 | 5 | 32 | Nitesh |  | Completed
firmware_wc_ltct | 2026-12-31 | Battery Mode Display | 3 | 3 | 35 | Nitesh |  | Completed
firmware_wc_ltct | 2026-12-21 | Self Diagnostic | 3 | 3 | 38 | Dev |  | Completed
firmware_wc_ltct | 2027-01-04 | Nameplate | 3 | 3 | 41 | Nitesh |  | Completed
firmware_wc_ltct | 2027-01-11 | Instantaneous Parameter | 52 | 52 | 93 | Nitesh |  | Completed
firmware_wc_ltct | 2027-01-15 | Rising Demand | 8 | 8 | 101 | Nitesh |  | Completed
firmware_wc_ltct | 2027-01-22 | Maximum Demand | 10 | 10 | 111 | Nitesh |  | Completed
firmware_wc_ltct | 2027-01-28 | Block Load | 22 | 22 | 133 | Nitesh |  | Completed
firmware_wc_ltct | 2027-02-04 | Daily Load | 10 | 10 | 143 | Nitesh |  | Completed
firmware_wc_ltct | 2027-01-01 | Billing Data | 50 | 50 | 193 | Dev |  | Completed
firmware_wc_ltct | 2027-01-08 | TOD Data | 23 | 23 | 216 | Dev |  | Completed
firmware_wc_ltct | 2027-02-09 | MD Reset Button | 4 | 4 | 220 | Nitesh |  | Completed
firmware_wc_ltct | 2027-02-15 | Digital Input | 9 | 9 | 229 | Nitesh |  | Completed
firmware_wc_ltct | 2027-02-18 | Tampers Voltage Related | 16 | 16 | 245 | Nitesh |  | Completed
firmware_wc_ltct | 2027-02-23 | Tampers Current Related | 11 | 11 | 256 | Nitesh |  | Completed
firmware_wc_ltct | 2027-02-25 | Tamper Other Related | 10 | 10 | 266 | Nitesh |  | Completed
firmware_wc_ltct | 2027-02-26 | Tamper Non-Rollover | 1 | 1 | 267 | Nitesh |  | Completed
firmware_wc_ltct | 2027-01-12 | Event Power Related | 2 | 2 | 269 | Dev |  | Completed
firmware_wc_ltct | 2027-01-22 | Event_Transaction Related | 48 | 48 | 317 | Dev |  | Completed
firmware_wc_ltct | 2027-02-02 | GPRS Testing | 15 | 15 | 332 | Dev |  | Completed
firmware_wc_ltct | 2027-02-08 | Push Notification ESWF | 22 | 22 | 354 | Dev |  | Completed
firmware_wc_ltct | 2027-02-12 | Firmware Upgrade | 22 | 22 | 376 | Dev |  | Completed
firmware_wc_ltct | 2027-03-02 | Functions | 7 | 7 | 383 | Nitesh |  | Completed
firmware_wc_ltct | 2027-02-16 | Interruption | 4 | 4 | 387 | Dev |  | Completed
firmware_wc_ltct | 2027-02-19 | Chattering | 11 | 11 | 398 | Dev |  | Completed
firmware_wc_ltct | 2027-03-04 | Calibration | 3 | 3 | 401 | Nitesh |  | Completed
firmware_wc_ltct | 2027-02-23 | Harmonics | 7 | 7 | 408 | Dev |  | Completed
firmware_wc_ltct | 2027-03-09 | Apparent Calculation | 11 | 11 | 419 | Nitesh |  | Completed
firmware_wc_ltct | 2027-03-12 | DLMS Association & Push | 17 | 17 | 436 | Nitesh |  | Completed
firmware_wc_ltct | 2027-03-18 | AC Chopping | 20 | 20 | 456 | Nitesh |  | Completed
firmware_wc_ltct | 2027-02-26 | DC Injection & Pulsating | 16 | 16 | 472 | Dev |  | Completed
firmware_wc_ltct | 2027-03-01 | Compartment | 1 | 1 | 473 | Dev |  | Completed
firmware_wc_ltct | 2027-03-19 | Tamper Configuration | 3 | 3 | 476 | Nitesh |  | Completed
meter_setu | 2026-08-19 | LG-005, LC-001, LC-013 | 3 | 3 | 3 | Shruti Singh | Executed — 2 Passed, 1 Failed | Completed
meter_setu | 2026-08-26 | LC-003 | 1 | 1 | 4 | Shruti Singh | Executed — Passed | Completed
meter_setu | 2026-09-03 | TC-001, TC-002, INT-008 | 3 | 3 | 7 | Shruti Singh | Executed — All Passed | Completed
meter_setu | 2026-09-04 | TC-011 | 1 | 1 | 8 | Shruti Singh | Executed — Passed | Completed
meter_setu | 2026-09-07 | LC-002, LC-006, LC-022 | 3 | 3 | 11 | Shruti Singh | Executed — 2 Passed, 1 Failed | Completed
meter_setu | 2026-09-10 | LC-004, LC-014 | 2 | 2 | 13 | Shruti Singh | Executed — 1 Passed, 1 Failed | Completed
meter_setu | 2026-09-18 | TC-003 | 1 | 1 | 14 | Shruti Singh | Executed — Passed | Completed
meter_setu | 2026-09-21 | SEC-002, LC-015, VAL-002, VAL-004 | 4 | 4 | 18 | Shruti Singh | Executed — All Passed | Completed
meter_setu | 2026-09-22 | LC-025, LC-026, LC-027, LC-028, LC-029 | 5 | 5 | 23 | Shruti Singh | Executed — All Passed | Completed
meter_setu | 2026-09-25 | LG-004, LG-006, TC-004, NEG-001, SEC-004, MA-011 | 6 | 6 | 29 | Shruti Singh | Executed — All Passed | Completed
meter_setu | 2026-09-28 | LC-010, LC-011 | 2 | 2 | 31 | Shruti Singh | Executed — All Passed | Completed
meter_setu | 2026-09-30 | LG-001, LG-003, AU-003, MA-001, MA-002, MA-004, DB-002, LC-008, LC-009, AU-005, VAL-005, INT-010, INT-011, LC-021 | 14 | 14 | 45 | Shruti Singh | Executed — All Passed | Completed
meter_setu | 2026-10-01 | LC-016, LC-018 | 2 | 2 | 47 | Shruti Singh | Executed — Metering Mode & MD Reset controls added in v1.2.20 | Completed
meter_setu | 2026-10-06 | INT-001, VAL-003, LG-010, LG-002, TC-005, MA-006, DB-001, NEG-006, INT-009, LC-005, DB-003, NEG-003, MA-007, LC-007, LC-012, LC-019, LC-020, MA-008, MA-009 | 19 | 19 | 66 | Shruti Singh | Executed — known v1.2.20 defects fail LG-002, TC-005, MA-006, DB-001, NEG-006, INT-009, MA-007, LC-012 | Completed
meter_setu | 2026-10-14 | LC-030, LC-031, LC-038 | 3 | 3 | 69 | Shruti Singh | Executed — new event & accuracy cards in 14-Oct v1.2.20 build | Completed
meter_setu | 2026-10-22 | INT-002, MA-003, FW-001, FW-002 | 4 | 4 | 73 | Shruti Singh | Executed — 2 Passed (MA-003, FW-002), 1 Failed (FW-001: no phase type on FOTA card), INT-002 rerun pending; INT-001 fixed for new WFM entry | Completed
meter_setu | 2026-10-23 | MA-012, NEG-004 | 0 | 0 | 73 | Shruti Singh | Planned — Screen rotation & DLMS failure mid-read | Planned
meter_setu | 2026-10-26 | MA-013, INT-012 | 0 | 0 | 73 | Shruti Singh | Planned — Meter tabs & Target Host IP (known v1.2.20 defects) | Planned
meter_setu | 2026-10-27 | LC-032, LC-033 | 0 | 0 | 73 | Shruti Singh | Planned — All Profile Read fresh read & Smart Skip | Planned
meter_setu | 2026-10-28 | LC-034, LC-036 | 0 | 0 | 73 | Shruti Singh | Planned — Smart Skip cache expiry & corrupt cache file | Planned
meter_setu | 2026-10-29 | LC-037, LC-023 | 0 | 0 | 73 | Shruti Singh | Planned — Cache per meter & per-meter Utility Settings controls | Planned
meter_setu | 2026-10-30 | DB-004, DB-005 | 0 | 0 | 73 | Shruti Singh | Planned — Offline CSV save & offline queue | Planned
meter_setu | 2026-11-02 | DB-006, DB-007 | 0 | 0 | 73 | Shruti Singh | Planned — Upload deletes local file & network loss during upload | Planned
meter_setu | 2026-11-03 | ST-001 | 0 | 0 | 73 | Shruti Singh | Planned — Background sync on internet restore | Planned
meter_setu | 2026-11-03 | All 124 cases | 0 | 0 | 73 | Shruti Singh | Planned — Full regression + DLMS verification + final report/email | Planned
meter_setu | TBD | LG-007, LG-008, LG-009, AU-001, AU-002, AU-004, AU-006, SEC-001, SEC-003, NEG-002, INT-003, INT-004, INT-005, INT-006, INT-007, TC-006, TC-007, TC-008, TC-009, TC-010, ST-002, LC-017, LC-024, LC-035, VAL-001, FW-003, FW-004, FW-005, FW-006, FW-007, FW-008, FW-011 | 0 | 0 | 73 | Shruti Singh | On hold (30) — needs other-flavour APKs, Firebase config, Android 12 image, backend support, write/flash approval, WFM tickets that complete on the bench | Planned
wfm | 2026-08-06 | Login Module | 14 | 14 | 14 | Shruti Singh | Login module completed | Completed
wfm | 2026-08-09 | Dashboard Module | 5 | 5 | 19 | Shruti Singh | Dashboard module completed | Completed
wfm | 2026-08-11 | Ticket Report | 5 | 5 | 24 | Shruti Singh | Ticket Report completed | Completed
wfm | 2026-08-11 | Ticket Portal | 9 | 9 | 33 | Shruti Singh | Ticket Portal completed | Completed
wfm | 2026-08-13 | NOMC Portal | 6 | 6 | 39 | Shruti Singh | Planned | Planned
wfm | 2026-08-15 | QC Portal | 6 | 6 | 45 | Shruti Singh | Planned | Planned
wfm | 2026-08-16 | Manual Ticket | 4 | 4 | 49 | Shruti Singh | Planned | Planned
wfm | 2026-08-18 | Bulk Upload | 5 | 5 | 54 | Shruti Singh | Planned | Planned
wfm | 2026-08-20 | Exceptions | 5 | 5 | 59 | Shruti Singh | Planned | Planned
wfm | 2026-08-22 | Escalated Tickets | 5 | 5 | 64 | Shruti Singh | Planned | Planned
wfm | 2026-08-24 | Ticket Details | 6 | 6 | 70 | Shruti Singh | Planned | Planned
wfm | 2026-08-26 | Warehouse | 6 | 6 | 76 | Shruti Singh | Planned | Planned
wfm | 2026-08-27 | Factory File Upload | 3 | 3 | 79 | Shruti Singh | Planned | Planned
wfm | 2026-08-29 | Vendor Forward | 5 | 5 | 84 | Shruti Singh | Planned | Planned
wfm | 2026-08-30 | Vendor Return | 3 | 3 | 87 | Shruti Singh | Planned | Planned
wfm | 2026-09-01 | Vendor Material Inventory | 5 | 5 | 92 | Shruti Singh | Planned | Planned
wfm | 2026-09-03 | Material History | 4 | 4 | 96 | Shruti Singh | Planned | Planned
wfm | 2026-09-05 | Technician Management | 4 | 4 | 100 | Shruti Singh | Planned | Planned
wfm | 2026-09-06 | Vendor Profile | 4 | 4 | 104 | Shruti Singh | Planned | Planned
wfm | 2026-09-08 | Helpline 1912 Portal | 5 | 5 | 109 | Shruti Singh | Planned | Planned
wfm | 2026-09-09 | Productivity Report & Field Logs | 4 | 4 | 113 | Shruti Singh | Planned | Planned
wfm | 2026-09-11 | User Management | 6 | 6 | 119 | Shruti Singh | Planned | Planned
wfm | 2026-09-13 | Role & Module Permissions | 5 | 5 | 124 | Shruti Singh | Planned | Planned
wfm | 2026-09-15 | Geography & Category Management | 6 | 6 | 130 | Shruti Singh | Planned | Planned
wfm | 2026-09-17 | Action, Material Lifecycle & Material Type | 10 | 10 | 140 | Shruti Singh | Phase 1 completed | Completed
wfm | 2026-09-19 | Mobile App – Part 1 | 5 | 5 | 145 | Shruti Singh | Planned | Planned
wfm | 2026-09-22 | Mobile App – Part 2 | 5 | 5 | 150 | Shruti Singh | Planned | Planned
wfm | 2026-09-24 | Mobile App – Part 3 + Integration | 5 | 5 | 155 | Shruti Singh | Planned | Planned
wfm | 2026-09-26 | RBAC Module | 5 | 5 | 160 | Shruti Singh | Planned | Planned
wfm | 2026-09-29 | Validation Module | 5 | 5 | 165 | Shruti Singh | Planned | Planned
wfm | 2026-10-01 | Negative Testing – Part 1 | 5 | 5 | 170 | Shruti Singh | Planned | Planned
wfm | 2026-10-05 | Negative Testing – Part 2 | 5 | 5 | 175 | Shruti Singh | Planned | Planned
wfm | 2026-10-07 | User Onboarding & Concurrency | 5 | 5 | 180 | Shruti Singh | Planned | Planned
wfm | 2026-10-09 | SM-to-SM QC | 4 | 4 | 184 | Shruti Singh | Planned | Planned
wfm | 2026-10-12 | SLA & SDUI Builder – Part 1 | 5 | 5 | 189 | Shruti Singh | Planned | Planned
wfm | 2026-10-14 | SDUI, Ticket Source, Scheduled Tasks & Security | 5 | 5 | 194 | Shruti Singh | Planned | Planned
wfm | 2026-10-16 | Security, System Configuration & Return to Factory | 5 | 5 | 199 | Shruti Singh | Planned | Planned
wfm | 2026-10-19 | Return to Factory & Warehouse Configuration | 5 | 5 | 204 | Shruti Singh | Planned | Planned
wfm | 2026-10-21 | Warehouse Configuration & CIMI | 5 | 5 | 209 | Shruti Singh | Planned | Planned
wfm | 2026-10-23 | CIMI & Material Returns History | 5 | 5 | 214 | Shruti Singh | Planned | Planned
wfm | 2026-10-26 | Material Returns History, AWS & API Client | 5 | 5 | 219 | Shruti Singh | Planned | Planned
wfm | 2026-10-28 | API Client & App Updates | 5 | 5 | 224 | Shruti Singh | Planned | Planned
wfm | 2026-10-30 | Admin Vendor Management & Remaining Test Cases | 7 | 7 | 231 | Shruti Singh | Phase 2 completed | Completed
gomati_mdms_rms | 2026-08-17 | Initial Master Data Sync | 27 | 27 | 27 | Shanvi | 25 PASS, 2 FAIL | Completed
gomati_mdms_rms | 2026-08-18 | Initial Master Data Sync + Attribute Change | 23 | 23 | 50 | Shanvi | 18 PASS, 5 FAIL, 1 Not Automatable | Completed
gomati_mdms_rms | 2026-08-19 | Attribute Change + Accept Prepaid Recharge + Account Balance Reconciliation + Reconnection & Disconnection + Arrear Payment Sync + Accept Non-Energy Charges | 25 | 25 | 75 | Shanvi | 24 PASS, 1 FAIL, 1 Not Automatable | Completed
gomati_mdms_rms | 2026-08-20 | Non-Energy Charges Payment Sync + Postpaid-Prepaid Conversion + Smart Meter to Smart Meter Change + Prepaid Balance Enquiry + Normal to Net Meter Change + Normal to Net Bill Change + Multiplying Factor Change | 22 | 22 | 97 | Shanvi | 20 PASS, 2 FAIL, 5 Not Automatable | Completed
gomati_mdms_rms | 2026-08-21 | Multiplying Factor Change + Billing Data Sync + Meter Badge Number Validation + Cross-Cutting NFR + Meter Advising + SAT/SLA Acceptance Criteria | 9 | 9 | 106 | Shanvi | 5 PASS, 4 FAIL, 10 Not Automatable | Completed

## Completion_Plan
project_id | name | total_cases | automatable | duration_days | daily_avg | start_date | expected_completion | status
hes_sangai | Sangai | 164 | 158 | 48 | 3 | 2026-06-19 | 2026-08-18 | Delayed
hes_goamti | Gomati | 168 | 162 | 48 | 3 | 2026-06-19 | 2026-08-18 | Delayed
vee | Gomati / Sangai | 603 | 579 | 45 | 0 | 2026-07-10 | 2026-09-25 | Delayed
consumer_app | Gomati (Android) | 88 | 78 | 60 | 1.35 | 2026-07-09 | 2026-10-15 | Delayed
comms | Comms (4G / RF / IMG / DCU) | 86 | 40 | 18 | 3 | 2026-07-07 | 2026-09-15 | Delayed
firmware_single_phase | 1-Phase Meter Firmware | 806 | 806 | 150 | 5 | 2026-08-16 | 2026-11-18 | On track
firmware_wc_ltct | 3-Phase WC | 476 | 476 | 116 | 5 | 2026-12-17 | 2027-03-19 | Not started Yet
meter_setu | Gomati — Stage/Dev | 124 | 120 | 56 | 1.52 | 2026-08-18 | 2026-11-03 | ON TIME
wfm | WFM Portal Stage | 278 | 123 | 0 | 2026 | TBD | Automation is temporarily on hold due to the current priority assignment for Meter Setu App testing. WFM automation will resume after completion of the current assignment. | On Hold
gomati_mdms_rms | Gomati -MDMS-RMS | 131 | 108 | 5 | 26 | 2026-08-17 | Not Given | Delayed